## Sprint 1
Functional Testing Case Study
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report http://demowebshop.tricentis.com/ Module: REGISTRATION, LOGIN & BUY ITEMS
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Depndacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Demo web shop is the sample online application for buying items It supports various functionalities such as user registration, login, searching for a product, add items to cart and payments. It is developed by Tricentis. It supports multiple browsers such as IE, Firefox, Chrome. In scope Functionality: Demo webshop provides following functionalities to the end user : 1. Registration Page : Validate the Firstname, Lastname, Email, Password, Retype password on the page. 2. Login a. Email : validate all fieldsa with valid and invlaid data. b. Password : validate with all options - valid and invlaid; the forgot password link, Sign-up link 3. Search an item a. Search Product on various categories - Books, Electronics items, Apparels and shoes, Digital downloads, and Jewellary b. View the products availability c. Add to cart 4. Buy items a. Enter shipping address b. Enter billing address c. Enter the payment details d. Enter the mode of delivery e. Discount coupons 5. Confirm Booking a. Download and acknowledge the receipt Out of Scope Functionality: 1. Cancel the order 2. Any other functionalities Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing QA Suggestions:- 1) Localization Testing most important 2) Exchange Rate (That Means Gobal Currency values should show correctly as per selected currency) 3) UI Testing 4) Scenario based Testing such as basic, alternate etc.
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report
Sprint Day 5 | Sprint Evaluation

## User_Stories
Registration module by Nilesh Abhang
Issue Type | Summary
Epic 1 | Verify Registration functionality
Story 1 | As a new user, I should be able to register my details into the application, so that I can perform required activity
Task 1 | As a user I want to register my details to application in order to keep track of my activities
Subtask 1 | Create new account

## Test_Scenario
Registration module by Nilesh Abhang
TestScenarioID | Req. Ref. Doc. Index | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
TS_REG_001 | REQ_REG_001 | Verification to visit registration page from home page | State transition testing (Black box testing) | 1 | 1. To validate that user is able to redirect to the registration page by clicking on register link from homepage.
TS_REG_002 | REQ_REG_002 | Verification of gender selection while registration | Functional testing | 2 | 1. To validate that user is able to select gender while registration.
2. Only one radio but should be checked at once.
TS_REG_003 | REQ_REG_003 | Verification of alphanumeric characters and special symbols as firstname of user | Functional testing | 1 | 1. To validate that user is able to enter albhabets, numbers as well as special characters as firstname
TS_REG_004 | REQ_REG_004 | Verification of alphanumeric characters and special symbols as lastname of user | Functional testing | 1 | 1. To validate that user is able to enter albhabets, numbers as well as special characters as lastname
TS_REG_005 | REQ_REG_005 | Verification of alphanumeric characters and special symbols as lastname of user | Functional testing | 1 | 1. To validate that user is able to enter albhabets, numbers as well as special characters as lastname
TS_REG_006 | REQ_REG_006 | Verification of acceptance about valid email address as registration email | Functional testing | 2 | 1. To validate that system is accepting only valid email address according regular expression
2. To validate that system is verifying email is not registered already.
TS_REG_007 | REQ_REG_007 | Verification of alphanumeric characters and special symbols as password of user | Functional testing | 1 | 1. To validate that user is able to enter albhabets, numbers as well as special characters as password
TS_REG_008 | REQ_REG_008 | Verification of alphanumeric characters and special symbols as confirm password of user | Functional testing | 2 | 1. To validate that user is able to enter albhabets, numbers as well as special characters as confirm password
2. To validate that system comapres the password and confirm password field correctly.

## Test Case Template
Registration module by Nilesh Abhang
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
TC_Reg_001 | Gender_01 | User is having an active internet connection | To validate that user is able to register when gender is not selected. | 1.Open browser |  | Browser should be opened | Browser is opening | Pass
|  | User has mail which is not registered already |  | 2.Enter the url for website | http://demowebshop.tricentis.com/ | Homepage for the website should appear | Homepage is launching | Pass
|  | User can access web page for registration |  | 3.Click on "Register" link |  | We should redirected to the registration page | We are able to redirect to the registration page | Pass
|  |  |  | 4.Select gender | Gender : Not selected | Error message to select gender should appear | No error message is appearing | Fail
|  |  |  | 5.Enter first name | Admin | It should accept that firstname | System is accepting Admin as firstname | Pass
|  |  |  | 6.Enter last name | admin | It should accept that lastname | System is accepting admin as lastname | Pass
|  |  |  | 7.Enter email | admin10@gmail.com | It should verify that mail is not registered | As this mail is not registered hence system is accepting this mail | Pass
|  |  |  | 8.Enter password | Admin@123 | It should verify the strength of password | System is not verifying the strength of the password. | Fail
|  |  |  | 9.Enter confirm password | Admin@123 | It should verify that confirm password matches with password | System allows us to confirm password successfully. | Pass
|  |  |  | 10.Click on "Register" button |  | It should redirect us to the login page on successful registration or proper error message should be displayed in case of failure. | Generation of error messages and validation is not proper needs improvement. | Fail
TC_Reg_002 | Gender_02 | User is having an active internet connection | To validate that user is able to register when gender is selected. | 1.Open browser |  | Browser should be opened | Browser is opening | Pass
|  | User has mail which is not registered already |  | 2.Enter the url for website | http://demowebshop.tricentis.com/ | Homepage for the website should appear | Homepage is launching | Pass
|  | User can access web page for registration |  | 3.Click on "Register" link |  | We should redirected to the registration page | We are able to redirect to the registration page | Pass
|  |  |  | 4.Select gender | Gender : Male | Radio button for Male should be checked and set gender as Male | Radio button for Male is checked and gender is set as Male | Pass
|  |  |  | 5.Enter first name | Admin | It should accept that firstname | System is accepting Admin as firstname | Pass
|  |  |  | 6.Enter last name | admin | It should accept that lastname | System is accepting admin as lastname | Pass
|  |  |  | 7.Enter email | admin10@gmail.com | It should verify that mail is not registered | As this mail is not registered hence system is accepting this mail | Pass
|  |  |  | 8.Enter password | Admin@123 | It should verify the strength of password | System is not verifying the strength of the password. | Fail
|  |  |  | 9.Enter confirm password | Admin@123 | It should verify that confirm password matches with password | System allows us to confirm password successfully. | Pass
|  |  |  | 10.Click on "Register" button |  | It should redirect us to the login page on successful registration or proper error message should be displayed in case of failure. | Generation of error messages and validation is not proper needs improvement. | Fail

## Defect Report
Registration module by Nilesh Abhang
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status
DF_REG_001 | Gender | User is allowed to register without selecting the gender | Medium | Nilesh Abhang | to-Do
DF_REG_002 | Firstname | The firstname field accepts special characters and numbers | Medium | Nilesh Abhang | To do
High
DF_REG_003 | Lastname | The lastname field accepts special characters and numbers | Medium | Nilesh Abhang | To do | Medium
DF_REG_004 | Email | The email validation with OTP is not implemented yet. | High | Nilesh Abhang | To do | Low
DF_REG_005 | Password | System is not able to measure strength of password and accepts easy passwords which might causes issues with security. | High | Nilesh Abhang | To do

## RTM
Registration module by Nilesh Abhang
S no. | Req_id | Epic no. | Story no. | Scenerio no. | Scenerio Description | Test case no. | Test Case Description | Execution Status | Defect _id | Defect Status
1 | 1 | 1 | 1 | TS_REG_002 | Verification of gender selection while registration | TC_Reg_001 | To validate that user is able to register when gender is not selected. | Fail | DF_REG_001 | In progress
[6 empty] | TC_Reg_002 | To validate that user is able to register when gender is selected as male | Pass
[6 empty] | TC_Reg_003 | To validate that user is able to register when gender is selected as male | Pass
2 | 2 | 1 | 1 | TS_REG_003 | Verification of alphanumeric characters and special symbols as firstname of user | TC_Reg_004 | To validate that user is able to register when firstname is empty. | Pass
[6 empty] | TC_Reg_004 | To validate that user is able to register when firstname contains numbers and special characters. | Fail | DF_REG_002 | In progress
[6 empty] | TC_Reg_006 | To validate that user is able to register when firstname does not contains numbers and special characters. | Pass
3 | 3 | 1 | 1 | TS_REG_004 | Verification of alphanumeric characters and special symbols as lastname of user | TC_Reg_007 | To validate that user is able to register when lastname is empty. | Pass
[6 empty] | TC_Reg_008 | To validate that user is able to register when lastname contains numbers and special characters. | Fail | DF_REG_003 | In progress
[6 empty] | TC_Reg_009 | To validate that user is able to register when lastname does not contains numbers and special characters. | Pass
4 | 4 | 1 | 1 | TS_REG_006 | Verification of acceptance about valid email address as registration email | TC_Reg_010 | To validate that user is able to register when email is in invalid format. | Fail | DF_REG_004 | In progress
[6 empty] | TC_Reg_011 | To validate that user is able to register when email is already registered. | Pass
[6 empty] | TC_Reg_012 | To validate that user is able to register when email is valid and not registered already. | Pass
5 | 5 | 1 | 1 | TS_REG_008 | Verification of alphanumeric characters and special symbols as confirm password of user | TC_Reg_013 | To validate that user is able to register when password is simple. | Fail | DF_REG_005 | In progress
[6 empty] | TC_Reg_014 | To validate that user is able to register when password and confirm password are not equal. | Pass

## Sprint 2
Automation Testing Case Study
Following website is given for Automating Testing using Selenium Automation Page Factory/POM, TestNG & BDD Framework (using Cucumber)
Url: http://phptravels.net/
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 | 1. Identify the Manual Test Cases that you want to automate. | 1. Creation of Project Structure
| 2. Plan the flow of application that you want to test using automation test scripts. | 2. Creation of Feature File.
3. Create a Maven Project - Associate required libraries with the Maven Project
4. Configure required dependencies like Selenium WebDriver, TestNG / Junit, Cucumber etc. in POM.xml
5. Creation of Feature File
Sprint Day 2 | 1. Create the required Feature files with relevant scenarios (User Stories) using Gherkin continue. | 1. List of Feature Files :
| · Use Scenario Outline & Examples to implement Parametrization in Feature File | 2. List of Test Cases :
| 2. Implement Page Factory or Object Repository (XML/Property File) to identify and store all the web elements. | 3. Prioritization of tests :
| · Use all types of Locators | 4. Test Runner class Parameters
| · Ensure appropriate usage of Selenium Web Driver API objects and import statements | 5. Report File Names
3. Design the test runner class
Sprint Day 3 | 1. Implement parametrization using apache POI | 1. Parametrization Sample Data :
| 2. Implement TestNG for generating reports and XML file for parallel execution of test suite | 2. Report File Names
| 3. Generate Step Definitions and write the Tests addressing all the functional requirements. | 3. Generating Step Defination File
Sprint Day 4 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements | 1. Detail Test Script in Step Definitions
| · Implement Assertions/Verifications using TestNG | 2. Feature File- Test Case – PF/OR collation in an Excel sheet
· Use appropriate wait statements
· Handle new windows, popup’s, navigations
2. Ensure implementation of good programing practices
· Variable, Function & procedure naming convention
· Usage of comments
· Code Indentation
Sprint Day 5 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements Continue | 1. Detail Test Script in Step Definitions
2. Feature File- Test Case – PF/OR collation in an Excel sheet
Sprint Day 6 | 1. Generate TestNG/XML Test report mentioning pass/fail status.
1. Test Reports
Sprint Day 7 | 1. Jenkins Implimentation 2. Project Closure | 1. Create build using Jenkins
Sprint Day 8 | Sprint Evaluation